NOTICE

ON PRICE QUOTATION

This text of the notice is approved by decision of the the Price Quotation Commission "2" of "26" 09 2025 and is published pursuant to Article 27 of the Law of the Republic of Armenia "On procurement"

Code of the Price Quotation EQ-BMKhAshDzB-26/1

The contracting authority Yerevan municipality, located at the following address: 1 Argishti Str, Yerevan, RA, gives notice for an urgent price quotation which shall be carried out in one stage, through Armeps (website www.armeps.am) system of electronic procurement.

The participant selected as a result of this procedure will be invited, in accordance with the established procedure, to conclude a contract for consulting work on the preparation of design estimates for a cable car from the administrative district of Yerevan city center to the Nor Nork administrative district in accordance with international standards and best practices (hereinafter referred to as the contract).

Pursuant to Article 7 of the Law of the Republic of Armenia "On procurement", any person, irrespective of the fact of being a foreign natural person, an organisation or a stateless person, shall have equal right to participate in this tender.

The qualification criteria for the persons ineligible to participate in the tender, as well as for bidders, and the documents to be submitted for evaluation of those criteria shall be established by the invitation for this procedure.

The selected bidder shall be determined by the principle of preference of the participant who received the highest rating for the offered price and non-price conditions established by the invitation.

In case of a request to provide the invitation electronically, the contracting authority shall ensure the free of charge provision of the invitation electronically within the working day following the date of receipt of the application.

The bids for the tender must be submitted electronically, through Armeps (www.armeps.am) system of electronic procurement, by 11:00 am 30.10.2025. The bids may, in addition to Armenian, also be submitted in English or Russian.

The bid urgent opening will take place electronically, through Armeps system of electronic procurement, at 11:00 am 30.10.2025.

The appeal of this procedure is carried out in accordance with the procedure established by the Law of the Republic of Armenia "On Procurement" and the Civil Procedure Code of the Republic of Armenia.

For receiving additional information concerning this notice, you may apply to 
G. Muradyan

Secretary of the Evaluation Commission.

Telephone 011514373

E-mail gor.muradyan@yerevan.am

Contracting authority Yerevan municipality

Procurement of consulting services for the preparation of design and cost estimate documentation for a cableway from Kentron administrative district of Yerevan to Nor Nork administrative district, in accordance with international standards and best practices

| № | Code provided by the procurement plan according to the classification (CPV) | Technical Specification | Unit of Measurement | Total Cost | Total Quantity | Project Address | Execution Period |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | 71241200/825 | To ensure convenient, unobstructed, fast, and environmentally friendly passenger transportation from the city center of Yerevan to the Nor Nork and Avan administrative districts, thereby unloading the road network in this direction (mainly Myasnikyan and Gay avenues). As a secondary goal, the ropeway may also serve as a tourist attraction. The starting station of the ropeway is planned near the “Yeritasardakan” metro station, and the final station — in the 2nd block of Nor Nork, adjacent to “Mega Mall.” The ropeway must provide a capacity of at least 3,000 passengers per hour in each direction. Ropeway type — gondola lift, intended for public transport, using cabins with a minimum capacity of 10 passengers. The starting and final stations must be integrated into the city’s route network, and the ticketing system must be unified. When designing the stations, their elevation must take into account the crossing of the ropeway with adjacent buildings. The program is planned to be implemented within 18 months from the date the contract enters into force, in two main stages. 1.The winner of the tender must develop the ropeway alignment, select land plots for the starting and final stations, as well as for the necessary towers along the route, collect baseline data, and carry out geodetic works. Based on these, the final alignment and land allocation schemes must be submitted to the Municipality for approval. Land selection must be made from community-owned and unencumbered plots, except when the Municipality agrees to initiate a process of recognizing and implementing an overriding public interest to confirm the optimal alignment. The Yerevan Municipality reviews and approves the alignment and land allocation schemes within one month after receiving them. In case of objections, the Municipality proposes modifications within the same period, after which the revised alignment and land allocation schemes are deemed approved. After approval of the alignment and land allocation schemes, the winner of the tender must, within one month, prepare the ropeway construction sketch project and submit the necessary documents to the Municipality for obtaining an architectural and planning assignment (APA). The Municipality, upon review, issues the APA within the timeframe established by law or proposes modifications, after acceptance of which the APA is issued. If recognition and implementation of overriding public interest is required on the allocated lands, the Municipality immediately initiates these procedures as defined by law, ensuring clearance of the territories. Until this work is completed and the lands are vacated, the contractor’s work is considered completed and delivered for Stage 1, the contract is suspended, and it resumes after completion of the land clearance, with the contract duration mechanically extended accordingly. Together with the APA, the winner of the tender is provided with the technical conditions for the necessary infrastructure (electricity, gas, water), with the required capacities to be defined within the APA package. 2.The winner of the tender must develop the ropeway construction project documentation in accordance with the APA requirements, arrange the prescribed expert reviews, and obtain all necessary approvals. The Yerevan Municipality shall support the winner of the tender in the approval process of the project documentation both in state agencies and in public utility providers. The winner of the tender shall submit to the Municipality all documents required by law to obtain a construction permit. This stage must be completed within one year from the date of obtaining the APA. Stage 1 duration — 6 months, payment — 35% of the contract price. Stage 2 duration — 1 year (after Stage 1), payment — 65% of the contract price. The winner of the tender must present justified work volumes based on conducted studies and measurements. The project must be developed in accordance with current standards. It is required to present: the relevant license, requirements for technical means, workforce, and professional qualifications, as well as a calendar schedule. The project must be submitted in 3 hard copies and on an electronic carrier. The project documentation must also be submitted in Russian. The project is subject to approval by the following organizations: - “Electric Networks of Armenia” CJSC - “Veolia Djur” CJSC - “Gazprom Armenia” CJSC, Yerevan Territorial Branch - RA Police, Road Police Service Payment for the second phase of work will be made after receiving a positive expert review. The participant must have at least 10 successfully implemented projects of ropeway design in an urban environment during the last five years. The participant must have a 1st class license in urban development in the following fields: 1)Transport routes (motor roads, railways, and airports, artificial structures such as bridges, tunnels, overpasses, viaducts, retaining walls, etc.); 2)Power supply (internal and external power supply and lighting networks, power supply systems, photovoltaic and wind power plants). | dram (AMD) |  | 1 | Yerevan | The Contract (in case the necessary financial resources are available – the concluded agreement) shall be valid for 18 months from the date of its entry into force. |